## Slide 1: Learning Session 1 Improvement Projects Participant Presentation Template

## Slide 2
The presence of the Laboratory African Regional Collaboration (LARC) logo on slides
indicates that content (in whole or in part) originates with the LARC Program

## Slide 3: Background
Focus of improvement project:
TB/ HIV diagnostic cascade step/gap
Facility Name
Speaker Name, Title,
Date
LARC Participant Presentation Template

## Slide 4: Project Team
List the members of the team & team member roles
  Include photo of CLICQ! team
LARC Participant Presentation Template

## Slide 5: Facility Information / Background
If possible:
Photo of facility and staff
Brief description of the facility
- # of ART patients on TPT
- # of TB patients
- # of TB diagnostic tests
performed
- Any other useful statistics
LARC Participant Presentation Template

## Slide 6: Stakeholder Analysis
Details of clients/ customers associated with the project.
LARC Participant Presentation Template

## Slide 7: Elevator Speech
This project is about _________________________________________
As a result of these efforts, (What will your project actually accomplish?)
It’s important because we are concerned about:
___(Big Picture Here)_________________
____________________
Success will be measured by showing improvement in:
____________________
____________________
What we need from you –
___(Describe to whom you are presenting the “ask”. What do you need from this person? Or organization?)___________________________
LARC Participant Presentation Template

## Slide 8: Process Mapping
Process Step | What Happens & where? | Who is responsible? | Duration | Documents needed | Opportunity for Improvement
(Show your process table. Provide sufficient detail of the entire process. Highlight the area(s) for improvement.)
LARC Participant Presentation Template

## Slide 9
Define
Measure
Analyze
Improve
Control
Gap (Problem Statement):
  Share your problem – (15 words or less, if possible)
LARC Participant Presentation Template

## Slide 10
Metric Selected
  Numerator/Denominator
Baseline Data
  Give current numerator/ current denominator and the percentage
Define
Measure
Analyze
Improve
Control
LARC Participant Presentation Template

## Slide 11
Data Collection Process
  Data Collection Tool
    List or insert picture (if available) of any data collection tool that was used for your project
  Data Collection Plan
    How many data points for baseline?
    Timeframe of data collection. How frequently did you collect your data? – entry & project data?
  Data Run Chart or Histogram
    Present the collected metric at regular timepoints that track progress
Define
Measure
Analyze
Improve
Control
LARC Participant Presentation Template

## Slide 12
Materials/ Supplies
Problem
Process
People
Environment
Policy/
Procedure
Equipment
Root cause - Insert picture/diagram of your fishbone diagram or other tool used. Circle your root cause.
Define
Measure
Analyze
Improve
Control
LARC Participant Presentation Template

## Slide 13: Impact / Effort Grid: A Tool for Prioritizing Opportunities
A tool to rank order potential solutions according to degree of impact and amount of effort
WHY
Allows input from the team, especially those who know the process first-hand, on the potential solutions
Provides an organized process to elicit thoughtful discussion and consensus on the potential impact of a solution and the degree of effort required to create that impact
Allows prioritization of potential solutions
LARC Learning Session I PowerPoint

## Slide 14: Impact / Effort Grid – A Tool for Prioritizing Opportunities
EFFORT
Easy to Do Difficult to Do
Projects: Detailed planning and work
Just Do It
Maybe some day
Just Do It if Impactful
Major
Improvement
Minor
Improvement
IMPACT
Define
Measure
Analyze
Improve
Control
LARC Participant Presentation Template

## Slide 15
Just Do Its
  Include lists and/or photos of Just Do Its completed
Define
Measure
Analyze
Improve
Control
LARC Participant Presentation Template

## Slide 16
Small Test of Change (PDSA #1)
ACT
PLAN
DO
STUDY
PDSA – Describe in Detail your PDSA.
Did you Adopt, Adapt or Abandon?
Define
Measure
Analyze
Improve
Control
LARC Participant Presentation Template

## Slide 17
Small Test of Change (PDSA #2)
ACT
PLAN
DO
STUDY
Define
Measure
Analyze
Improve
Control
PDSA – Describe in Detail your PDSA.
Did you Adopt, Adapt or Abandon?
LARC Participant Presentation Template

## Slide 18: Challenges
Share challenges. What did the team do to address the challenges?
Challenges | How challenges were addressed
1 | 1
2 | 2
3 | 3
4 | 4
5 | 5
LARC Participant Presentation Template

## Slide 19: Lessons Learned
Share lessons learned.
LARC Participant Presentation Template

## Slide 20: Action Plan
Action Plan – Share your action plan, if you have any additional actions to complete.
Topics / Goals | Action Item | By Whom? | By When?
LARC Participant Presentation Template

## Slide 21
Identify Stakeholders
Team Formation
Map the Process (Current)
ID/ Prioritize Opportunities
  Project Outline
Baseline Metrics - Data
Collection Tool/Plan
Action Plan
Elevator Speech
VOC Information
Root Cause Analysis
1 Rapid/Small Test of Change (PDSA)
Presentation
Learning Session 1 Deliverables
DEFINE/ MEASURE/ ANALYZE
LARC Participant Presentation Template

## Slide 22
Questions?